## Now
	Install perl modules on antix vm
	Go over textfiles from textfiles.org
	Bug: When new user posts for the first time, author directory is not accessible until next indexing

1

1

			Move existing cache references to these subs

## Backlog
	Add “Report” button and “Should be removed immediately” button.	Remove immediately sub	Parse in access log	Add PGP bonuses later
	Prettify the interface, add a couple of catchy images.
	Add more actions that the user can do through the web interface	Build new router for actions?
	Add to the administration manual	How to name gpg’ed directory?
	Fix signing the address of the posting site	Semi-fixed, still gives the wrong address.	Work out the port assignments
	Add mirroring functionality	Site list	Access sites through curl?	Merge textfiles where?
	Verify all posts on the posting site before displaying them	How?
	Add backend for administration	See actions/router	Separate onion? Password?
	Implement configuration via access.log and Perl	Configure what?
	Create routing system	Create new perl file that handles /actions/	Move the truncating of access log to access.sh
	Add a “Destroy” button somewhere
1	Add referring sites directory	Add referrer counting in access.pl	Parse only onion sites	Make a links directory with text files of .onion.lnk with description inside
	Architect and add links page	Use address.onion.lnk with description inside	Add special case in indexer to link .onion.lnk	Add ability to ping sites and see if they’re up
	Add handling for new empty GPG directories	How to add new entries to indexer?	Either auto-index subdirs -or- add a line to indexes.sh	Find a solution for symlinking index.pl everywhere, probably move it to dev
	How do GPG posts get listed on the main timeline?	put everything into subdirs, anon in its own, then symlink from top
	Retrieve GPG keys
	Update .nfo for titles of sub-pages
	Switch to using full key ID for directories?
	Commands should be queued for admin approval before execution
	Think about routing using rewrites, cookies?
	Login via cookie set via /profile/password
	Routing via cookie
	Sorting into folders: if current date doesn’t match the part before the underscore, put it into that folder
	Fix footer links
	To address a message to any known public key just post it	Use pgp to get recipient key, match against db
	Database integration? Sqlite? Postgres? Necessary?
	Limit post count to below performance hit threshold	Do some performance testing with 20k files
	Are you sure you want to browse with javascript enabled?	Yes=hide message
	What is the MVP for publishing plays with readable printout?
	Install instructions go into an install file
	Polls!!!!	Questions in a series
	Switch to Mongoose for web server	Consolidate everything into one tree	Make Mongoose write an access log	Adjust access.pl to use new access log
	Make a script for restarting SWS and rotating logs
	Add log writing to mongoose LOG() function
	Add support for sort.lst, which specifies which items to list at the top, in the order provided
	Newest content page
1	Pagination and/or board size limit
	Link user pages to anchored comment	Depends on anchor generation
	Crumbtrail at the header of the page
1	Add HTTP headers for conservative caching
	Make a blockchain	Calculate sha sum of all the txt names and their sums	Write to .txt.chain for new post	How to perform verification?
	Review required sub-modules, look for cli replacements
1	Write slurp.pl	Slurp every folder I have myself	And put it into $dir/incoming
	Figure out how to use ffmpeg to generate series of thumbnails for a video
	Figure out how to embed audio
	Is a return message system necessary?
	Add support for pre-fetching of sub-pages
	Automate .zip generation for entire site, including root dir	Make several zip distros, incl/excl library and other heavy dirs
	Login workflow	Post your public key	Login link is generated, encrypted, and posted to /login/<key> page	Going to /login/<key>/<secret> sets session cookie	Add cookie to access log? Or just rewrite /action/blah to ..../cookie/action/blah
	Generate support pages for wav files	Include <audio> tag
	Get author pages sorted, at least with filesystem times	Query the filesystem (astat?)	Save them to hashes	Reorder the file array	Make this into a sub
	Is it possible to involve a genetic algo in page generation?
	Public-private messaging board	Add a separate zip for easy downloading
	Brainstorm pruning strategies
	Add zipping of each directory	Exclude subdirectory zips from each archive	Link from index files
	Add check for board.nfo when looking for gracias.html
	Make FAQ more accessible wrt identity management	Break each long answer into several sections
	Use hashes to detect duplicate posts
	(bug) Some pages' generated counter is incremented twice each time
	Implement commands for signed messages	vote	tag	delete	destroy	username
	Think about threading	Messages need a parent ID	Fix date parsing?	Folders for threads?
	Deployment scripts	Fix prod to match dev	Copy files	Debug apache2
	Command parser	Dispatch table	Make indexer write command.html with proper token
	Break out individual message printing into function	Integrate function into individual .html generators
	Remove dependency on URI/Encode.pm
	Integrate Droopy for uploading files	Only for trusted users
	Add handling for expired keys
	Games?	connect4
	Add warning if unable to truncate access log
	Fix newest items list generator
	(bug) Pubkey upload is not added to author page
	Create a LOG() function with timestamp
	Ensure that onion address is in access log
	Make a separate onion per user
	Write functions for adding/removing onions
	Write subs for GetCache and PutCache	Use a dedicated cache/ dir	Move existing cache references to these subs
	Write installation section of manual
	List public keys somewhere
	Add faq.html and other starter files to git	This means either removing html/ from gitignore or adding them to templates
	Update FAQ to include info on how to create a user account
	Make index.pl write to a specified file instead of print to stdout	Put everything into a function	Give the function a parameter
	Figure out how to do date conversions	Extract date from DDMMMYYYY	Save date as YYYYMMDD	Extract time	Save time
	Add a directory of hashes of submitted texts, so that new submissions can be checked against all of them at once, even if they are in different directories	Use command-line sha256sum
	Ensure that onion address is in access log
	Make a separate onion per user
	Write functions for adding/removing onions
	Write subs for GetCache and PutCache	Use a dedicated cache/ dir
	Write installation section of manual
	List public keys somewhere
	How to deal with duplicate usernames?
	Move caches to cache directory? or just add to .gitignore?	Make GetCache	Make PutCache
	How to list text files better?
	Add provision for regenerationg .cache files when they expire (or expire them manually)

## Log
√	Fresh raspbian
√	Install apache2, tor, sshd
√	Configure torrc
√	Copy scripts into dev
√	ln -s /home/pi/dev/forma.html /var/www/html/text/forma.htm
√	apt-get install dh-make-perl
√	dh-make-perl --build --cpan URI::Encode
√	Add crontab for moving the access log to our directory (root)	﻿* * * * * cat /var/log/apache2/access.log >> /home/ilya/logs/access.log ; truncate -s 0 /var/log/apache2/access.log
√	Add crontab for /home/pi/dev/access.pl and indexes.pl (user)
√	mongoose: compile SWS with debug on and htroot=./html
√	Decouple posting from /text/ dir. Make it post to current dir. Dir = board/thread/topic
√	Copy install on another hostname and test
√	Set apache to write access log to ./logs/
√	Add header with site links
√	Post to whichever directory the form is in
√	Build .lst files during indexing
√	Write user pages
√	Add links to author page to indexes
√	Test user pages basic
√	Create cron.pl to run all jobs at once
√	﻿AddDefaultCharset utf-8
√	Remove indexed files that no longer exist
√	Move $SCRIPTDIR into .nfo file
√	Make function that prints all items in a .list
√	Create a mode that links and describes files
√	Create a mode that makes a list of links
√	Figure out how to get the install path without config
√	Make a test cron job
√	Update “lockfile” path
√	Trim whitespace from new messages
√	Split it into a backend/ (scripts) and frontend/ (html) directory.
√	Add comments throughout index.pl
√	Make indexes.pl not call sorter.pl unless board.nfo is set
√	﻿AddType text/cache-manifest .mf
√	Make index.pl print text files only when in board mode
√	Increased submission limit to 2^13
√	apt-get install zip
√	Break menu out into a separate template that gets included twice
√	Add page generated counter
√	Use a temporary index file, then rename, to avoid blank pages
√	Fix bug that causes extra (invalid) entries in html/author/xxx.lst
√	Convert list of boards in access.pl to cached index file
√	Refactor all configs into one require’d file
√	Break out signature detection into a function
√	Remove hard-coded index directories from index.pl
√	Add title copying from ./$dir/title.nfo to ./$dir.nfo and vice versa
√	Make a list of links to publish
√	Remedy serving of half-generated files by doing a .tmp swap
√	(bug) New authors' author pages are not made
√	When printing signed message, check for existence of saved username for key
√	To set your username, post your public key
√	Use alias.nfo when writing titles for author pages
√	Refactor GPG parsing into separate file
√	Update GPG parser to display messages signed with an expired key
√	Add sorting to all boards, not just main /text/ board
√	Add $primaryColor to template
√	Split file link to htmlized version and “.txt” link
√	Cache GPG results to save CPU
√	Update message board’s .nfo file in parent dir to reflect message count
√	Create signup board for uploading public keys
√	Make an html_default in repo
√	Make scripts check for html/ and create it if not
√	Add border around comments
√	Fix broken links in clean install (menu)
√	Finish debugging after index.pl refactor
√	Generate a zip file for each directory that has makezip.nfo
√	Link the zip file at the bottom of the page
√	Fix errors introduced by zipping and gitting
√	Add admin/ to repo

## Tests
Homepage	10/17/17
Homepage has footer image
Boards	10/17/17
Post message	10/17/17
Post message, signed	10/17/17
Post message for admin	10/17/17
Horoscope	10/17/17
Counter	10/17/17

## Deploy
Apache	Create new hostname	Edit ports.conf	Add wisebody.conf
Tor	Add to torrc	Add to /var/lib/tor
Filesystem	Deploy	Create new dir
	Switch to new hostname

## Promo
base64 “secret” codes
invite tree
cards
wom

## Git
GetCache
PutCache
Exclude .cache files
Exclude .zip files?