## Now
Add handling for expired keys

## Backlog
Add “Report” button and “Should be removed immediately” button.	Remove immediately sub	Parse in access log	Add PGP bonuses later
Prettify the interface, add a couple of catchy images.
Rebuild another device, including WiFi portal	Need monitor+kb+power	Get help from Alex
Add more actions that the user can do through the web interface	Build new router for actions?
Add to the administration manual	How to name gpg’ed directory?
Fix signing the address of the posting site	Semi-fixed, still gives the wrong address.	Work out the port assignments
Add mirroring functionality	Site list	Access sites through curl?	Merge textfiles where?
Verify all posts on the posting site before displaying them	How?
Add backend for administration	See actions/router	Separate onion? Password?
Experiment with running an Ether blockchain	Split off into another project
Implement configuration via access.log and Perl	Configure what?
Create routing system	Create new perl file that handles /actions/	Move the truncating of access log to access.sh
Implement counters for page access
Add support for GPG – verify signature and move to subdir
Add a “Destroy” button somewhere
Add referring sites directory	Add referrer counting in access.pl	Parse only onion sites	Make a links directory with text files of .onion.lnk with description inside
Architect and add links page	Use address.onion.lnk with description inside	Add special case in indexer to link .onion.lnk	Add ability to ping sites and see if they’re up
Add handling for new empty GPG directories	How to add new entries to indexer?	Either auto-index subdirs -or- add a line to indexes.sh	Find a solution for symlinking index.pl everywhere, probably move it to dev
How do GPG posts get listed on the main timeline?	put everything into subdirs, anon in its own, then symlink from top
Improve readability
Sort messages with newest on top, sort by date modified
Retrieve GPG keys
Update .nfo for titles of sub-pages
Switch to using full key ID for directories?
Commands should be queued for admin approval before execution
Think about routing using rewrites, cookies?
Login via cookie set via /profile/password
Routing via cookie
Sorting into folders: if current date doesn’t match the part before the underscore, put it into that folder
Fix footer links
To address a message to any known public key just post it	Use pgp to get recipient key, match against db
Database integration? Sqlite? Postgres? Necessary?
Limit post count to below performance hit threshold	Do some performance testing with 20k files
Are you sure you want to browse with javascript enabled?	Yes=hide message
What is the MVP for publishing plays with readable printout?
Install instructions go into an install file
Polls!!!!	Questions in a series
Switch to Mongoose for web server	Consolidate everything into one tree	Make Mongoose write an access log	Adjust access.pl to use new access log
Make a script for restarting SWS and rotating logs
Add log writing to mongoose LOG() function
Add support for sort.lst, which specifies which items to list at the top, in the order provided
Newest content page
Update message board’s .nfo file in parent dir to reflect message count
Pagination and/or board size limit
Author name assignment by key fingerprint	First the backend?	Then the assignment via command
Link user pages to anchored comment	Depends on anchor generation
Crumbtrail at the header of the page
Add HTTP headers for conservative caching
Make a blockchain	Calculate sha sum of all the txt names and their sums	Write to .txt.chain for new post	How to perform verification?
Review required sub-modules, look for cli replacements
Fix newest files .lst generator
Write slurp.pl	Slurp every folder I have myself	And put it into $dir/incoming
Generate an individual .html file for each text file
Figure out how to use ffmpeg to generate series of thumbnails for a video
Figure out how to embed audio
Is a return message system necessary?
Add support for importing public key
Add support for pre-fetching of sub-pages
Automate .zip generation for entire site, including root dir	Make several zip distros, incl/excl library and other heavy dirs
Login workflow	Post your public key	Login link is generated, encrypted, and posted to /login/<key> page	Going to /login/<key>/<secret> sets session cookie	Add cookie to access log? Or just rewrite /action/blah to ..../cookie/action/blah
Generate support pages for wav files	Include <audio> tag
Get author pages sorted, at least with filesystem times	Query the filesystem (astat?)	Save them to hashes	Reorder the file array	Make this into a sub
Is it possible to involve a genetic algo in page generation?
Public-private messaging board	Add a separate zip for easy downloading
Brainstorm pruning strategies
Add zipping of each directory	Exclude subdirectory zips from each archive	Link from index files
Add check for board.nfo when looking for gracias.html
Make FAQ more accessible wrt identity management	Break each long answer into several sections
Use hashes to detect duplicate posts
(bug) Some pages' generated counter is incremented twice each time
Add a directory of hashes of submitted texts, so that new submissions can be checked against all of them at once, even if they are in different directories	Use command-line sha256sum
Implement commands for signed messages	vote	tag	delete	destroy	username
Think about threading	Messages need a parent ID	Fix date parsing?	Folders for threads?
Deployment scripts	Fix prod to match dev	Copy files	Debug apache2
Figure out how to do date conversions	Extract date from DDMMMYYYY	Save date as YYYYMMDD	Extract time	Save time
Command parser	Dispatch table	Make indexer write command.html with proper token
Cache GPG results
Break out individual message printing into function	Integrate function into individual .html generators
Remove dependency on URI/Encode.pm
Integrate Droopy for uploading files	Only for trusted users

## Log
√	Fresh raspbian
√	Install apache2, tor, sshd
√	Configure torrc
√	Copy scripts into dev
√	ln -s /home/pi/dev/forma.html /var/www/html/text/forma.htm
√	apt-get install dh-make-perl
√	dh-make-perl --build --cpan URI::Encode
√	Add crontab for moving the access log to our directory (root)	﻿* * * * * cat /var/log/apache2/access.log >> /home/ilya/logs/access.log ; truncate -s 0 /var/log/apache2/access.log
√	Add crontab for /home/pi/dev/access.pl and indexes.pl (user)
√	mongoose: compile SWS with debug on and htroot=./html
√	Decouple posting from /text/ dir. Make it post to current dir. Dir = board/thread/topic
√	Copy install on another hostname and test
√	Set apache to write access log to ./logs/
√	Add header with site links
√	Post to whichever directory the form is in
√	Build .lst files during indexing
√	Write user pages
√	Add links to author page to indexes
√	Test user pages basic
√	Create cron.pl to run all jobs at once
√	﻿AddDefaultCharset utf-8
√	Remove indexed files that no longer exist
√	Move $SCRIPTDIR into .nfo file
√	Make function that prints all items in a .list
√	Create a mode that links and describes files
√	Create a mode that makes a list of links
√	Figure out how to get the install path without config
√	Make a test cron job
√	Update “lockfile” path
√	Trim whitespace from new messages
√	Split it into a backend/ (scripts) and frontend/ (html) directory.
√	Add comments throughout index.pl
√	Make indexes.pl not call sorter.pl unless board.nfo is set
√	﻿AddType text/cache-manifest .mf
√	Make index.pl print text files only when in board mode
√	Increased submission limit to 2^13
√	apt-get install zip
√	Break menu out into a separate template that gets included twice
√	Add page generated counter
√	Use a temporary index file, then rename, to avoid blank pages
√	Fix bug that causes extra (invalid) entries in html/author/xxx.lst
√	Convert list of boards in access.pl to cached index file
√	Refactor all configs into one require’d file
√	Break out signature detection into a function
√	Remove hard-coded index directories from index.pl
√	Add title copying from ./$dir/title.nfo to ./$dir.nfo and vice versa
√	Make a list of links to publish
√	Remedy serving of half-generated files by doing a .tmp swap
√	(bug) New authors' author pages are not made
√	When printing signed message, check for existence of saved username for key
√	To set your username, post your public key
√	Use alias.nfo when writing titles for author pages
√	Refactor GPG parsing into separate file
√	Update GPG parser to display messages signed with an expired key
√	Add sorting to all boards, not just main /text/ board
	Add $primaryColor to template
	Split file link to htmlized version and “.txt” link

## Tests
Homepage	09/08/17
Boards	09/08/17
Post message	09/08/17
Post message, signed	09/08/17
Post message for admin	09/08/17
Horoscope	09/08/17
Counter

## Deploy
Apache	Create new hostname	Edit ports.conf	Add wisebody.conf
Tor	Add to torrc	Add to /var/lib/tor
Filesystem	Deploy	Create new dir
	Switch to new hostname

## Promo
base64 “secret” codes
invite tree
cards
wom